## Setup
Field | Value | Guidance
Template | Corrective-action register | Track a finding from immediate correction to cause and effectiveness review.
Process / register ID |  | Enter the actual context and identifier.
Register owner |  | Complete for your organization and meeting or register.
Review date / next review |  | Complete for your organization and meeting or register.
Status vocabulary |  | Complete for your organization and meeting or register.
Effectiveness review rule |  | Complete for your organization and meeting or register.
Version / access / retention review |  | Complete for your organization and meeting or register.
Use | Separate immediate correction from preventing recurrence. Close after the effectiveness review, not just implementation. | Template is blank; Fictional example shows sample wording.
Examples | Fictional training data only. | No real people, approvals or completed work are represented.
Dates | Use YYYY-MM-DD in date fields. | Preserve original commitments and record reasons for changes.
PDF | Printable blank form. | The editable formats provide more rows; insert additional rows as needed.
Privacy | Collect only information necessary for the purpose. | Apply your access and retention rules.
Origin | Original educational template, prepared 2026-10-02. | Adapt to your process; no certification or legal conformity is implied.

## Template
ID / finding / source | Immediate correction | Cause / corrective action | Owner | Due date | Status / evidence | Effectiveness test / date | Result / closure / reviewer

## Fictional example
ID / finding / source | Immediate correction | Cause / corrective action | Owner | Due date | Status / evidence | Effectiveness test / date | Result / closure / reviewer
CA-001 / Late access removal / Review R-04 | Remove the expired contractor access and test old links. | Missing end-date notice; add owner and reminder to departure process. | Admin lead | 2026-10-09 | Implementing / Request DEMO-011 | Review next 5 departures on 2026-11-06. | Pending; keep open until effectiveness is established.
CA-002 / Wrong revision issued / Review R-05 | Withdraw incorrect copy and notify recipients. | Ambiguous issue folder; require revision check before issue. | Document lead | 2026-10-12 | Investigating / Issue record DEMO-012 | Sample next 10 issues on 2026-11-09. | Pending / Quality lead