## Setup
Field | Value | Guidance
Template | Handover action register | Resolve missing asset information and record operational acceptance.
Facility / handover package |  | Enter the actual context and identifier.
Register owner |  | Complete for your organization and meeting or register.
Review date / target handover |  | Complete for your organization and meeting or register.
Status vocabulary |  | Complete for your organization and meeting or register.
Acceptance authority |  | Complete for your organization and meeting or register.
Version / access / retention review |  | Complete for your organization and meeting or register.
Use | Verify the actual asset and recipient access. This is a follow-up register, not a COBie exchange or acceptance certificate. | Template is blank; Fictional example shows sample wording.
Examples | Fictional training data only. | No real people, approvals or completed work are represented.
Dates | Use YYYY-MM-DD in date fields. | Preserve original commitments and record reasons for changes.
PDF | Printable blank form. | The editable formats provide more rows; insert additional rows as needed.
Privacy | Collect only information necessary for the purpose. | Apply your access and retention rules.
Origin | Original educational template, prepared 2026-10-02. | Adapt to your process; no certification or legal conformity is implied.

## Template
ID / asset / location | Missing item / requirement | Owner | Due date | Acceptance test | Status / blocker | Evidence / version | Accepted date / by

## Fictional example
ID / asset / location | Missing item / requirement | Owner | Due date | Acceptance test | Status / blocker | Evidence / version | Accepted date / by
HO-001 / AHU-001 / L01-PLANT | Correct model's operating manual is missing. | Mechanical lead | 2026-10-16 | Open manual, compare model and test operator access. | Open | DOC-021 pending
HO-002 / AHU-002 / L01-PLANT | Serial number must be checked on installed unit. | Site engineer | 2026-10-14 | Compare asset row with nameplate photograph. | Ready for review | DEMO-PH-002 / R01