## Setup
Field | Value | Guidance
Template | Project action register | Deliverables, dependencies, revised commitments and acceptance evidence.
Project / register ID |  | Enter the actual context and identifier.
Register owner |  | Complete for your organization and meeting or register.
Review date / next review |  | Complete for your organization and meeting or register.
Status vocabulary |  | Complete for your organization and meeting or register.
Date-change rule |  | Complete for your organization and meeting or register.
Version / access / retention review |  | Complete for your organization and meeting or register.
Use | Link the source decision and exact deliverable. A revised date needs a reason and agreement; retain the original commitment. | Template is blank; Fictional example shows sample wording.
Examples | Fictional training data only. | No real people, approvals or completed work are represented.
Dates | Use YYYY-MM-DD in date fields. | Preserve original commitments and record reasons for changes.
PDF | Printable blank form. | The editable formats provide more rows; insert additional rows as needed.
Privacy | Collect only information necessary for the purpose. | Apply your access and retention rules.
Origin | Original educational template, prepared 2026-10-02. | Adapt to your process; no certification or legal conformity is implied.

## Template
Action ID / source | Deliverable / acceptance test | Owner | Original due | Current due / change reason | Status / dependency | Evidence / reviewer | Accepted date / by

## Fictional example
Action ID / source | Deliverable / acceptance test | Owner | Original due | Current due / change reason | Status / dependency | Evidence / reviewer | Accepted date / by
ACT-031 / MTG-012-01 | D-014 R03 resolves coordination comment C-08. | Design lead | 2026-10-08 | 2026-10-08 | In progress / Mechanical response | D-014 R03 / Coordination lead
ACT-032 / MTG-012-02 | Supplier confirms the equipment delivery date in writing. | Procurement lead | 2026-10-09 | 2026-10-12; supplier delay agreed 2026-10-02 | Blocked / Supplier confirmation | Supplier response / Sponsor