## Setup
Field | Value | Guidance
Template | Team action register | Everyday commitments with one owner and a clear completion test.
Team / register ID |  | Enter the actual context and identifier.
Register owner |  | Complete for your organization and meeting or register.
Review date / next review |  | Complete for your organization and meeting or register.
Status vocabulary |  | Complete for your organization and meeting or register.
Closure rule |  | Complete for your organization and meeting or register.
Version / access / retention review |  | Complete for your organization and meeting or register.
Use | Keep one accountable owner. Preserve original dates; explain changes. Close only after the agreed result is accepted. | Template is blank; Fictional example shows sample wording.
Examples | Fictional training data only. | No real people, approvals or completed work are represented.
Dates | Use YYYY-MM-DD in date fields. | Preserve original commitments and record reasons for changes.
PDF | Printable blank form. | The editable formats provide more rows; insert additional rows as needed.
Privacy | Collect only information necessary for the purpose. | Apply your access and retention rules.
Origin | Original educational template, prepared 2026-10-02. | Adapt to your process; no certification or legal conformity is implied.

## Template
Action ID / source | Action / acceptance test | Owner | Original due | Current due | Status / blocker | Evidence / reviewer | Closed date / accepted by

## Fictional example
Action ID / source | Action / acceptance test | Owner | Original due | Current due | Status / blocker | Evidence / reviewer | Closed date / accepted by
ACT-001 / MTG-001-01 | Confirm support cover and publish reviewed rota. | Team lead | 2026-10-05 | 2026-10-05 | In progress | Rota draft / Coordinator
ACT-002 / MTG-001-02 | Revise reference guide; peer review confirms answers. | Analyst | 2026-10-08 | 2026-10-08 | Open | Guide revision / Team lead
ACT-003 / MTG-000-04 | Confirm training room booking. | Coordinator | 2026-10-01 | 2026-10-01 | Closed | Booking confirmation DEMO-03 / Team lead | 2026-10-01 / Team lead