## Setup
Field | Value | Guidance
Template | Project coordination minutes | Cross-discipline decisions and their effects on deliverables.
Project / meeting ID |  | Enter the actual context and identifier.
Date / time / time zone |  | Complete for your organization and meeting or register.
Chair / minute taker |  | Complete for your organization and meeting or register.
Attendees / disciplines |  | Complete for your organization and meeting or register.
Purpose / next coordination |  | Complete for your organization and meeting or register.
Version / approval / distribution |  | Complete for your organization and meeting or register.
Use | Reference the affected revision. Distinguish a coordination comment from an instruction or authorized change. | Template is blank; Fictional example shows sample wording.
Examples | Fictional training data only. | No real people, approvals or completed work are represented.
Dates | Use YYYY-MM-DD in date fields. | Preserve original commitments and record reasons for changes.
PDF | Printable blank form. | The editable formats provide more rows; insert additional rows as needed.
Privacy | Collect only information necessary for the purpose. | Apply your access and retention rules.
Origin | Original educational template, prepared 2026-10-02. | Adapt to your process; no certification or legal conformity is implied.

## Template
Item ID | Deliverable / revision | Issue / evidence | Decision / authority | Action / acceptance test | Owner | Due date | Action ID

## Fictional example
Item ID | Deliverable / revision | Issue / evidence | Decision / authority | Action / acceptance test | Owner | Due date | Action ID
01 | D-014 / R02 | Doorway clashes with service route. | Designer to coordinate; no construction release. | Submit R03 with clash response for review. | Design lead | 2026-10-08 | ACT-031
02 | Equipment schedule / R01 | Delivery date is unconfirmed. | Sponsor retains selection subject to confirmation. | Obtain supplier's written delivery commitment. | Procurement lead | 2026-10-09 | ACT-032