## Setup
Field | Value | Guidance
Template | Site coordination minutes | Location-specific observations, work constraints and inspection follow-up.
Site / meeting ID |  | Enter the actual context and identifier.
Date / time / conditions |  | Complete for your organization and meeting or register.
Chair / minute taker |  | Complete for your organization and meeting or register.
Attendees / contractors |  | Complete for your organization and meeting or register.
Work period / next meeting |  | Complete for your organization and meeting or register.
Version / approval / distribution |  | Complete for your organization and meeting or register.
Use | Use the separate urgent-hazard and statutory reporting procedures when needed. Minutes do not authorize unsafe work. | Template is blank; Fictional example shows sample wording.
Examples | Fictional training data only. | No real people, approvals or completed work are represented.
Dates | Use YYYY-MM-DD in date fields. | Preserve original commitments and record reasons for changes.
PDF | Printable blank form. | The editable formats provide more rows; insert additional rows as needed.
Privacy | Collect only information necessary for the purpose. | Apply your access and retention rules.
Origin | Original educational template, prepared 2026-10-02. | Adapt to your process; no certification or legal conformity is implied.

## Template
Item ID | Area / activity | Observation / reference | Constraint / agreed outcome | Action / inspection evidence | Owner | Due date | Action ID

## Fictional example
Item ID | Area / activity | Observation / reference | Constraint / agreed outcome | Action / inspection evidence | Owner | Due date | Action ID
01 | Plant room | Access route shown on SK-004. | Confirm route before delivery booking. | Photograph and verify clear delivery route. | Site manager | 2026-10-05 | ACT-041
02 | Level 1 services | Inspection request IR-022 remains open. | Hold concealment pending the required acceptance. | Arrange inspection and attach the outcome. | Trade supervisor | 2026-10-06 | ACT-042