## Meeting Setup
Field | Value | Guidance
Field | Value | Guidance
Meeting title | Weekly coordination meeting | Use a short title that makes the purpose searchable.
Project / workspace | Project Alpha | Use the same name as the project or workspace context.
Date | 2026-05-07 | Meeting date. Keep the file date format consistent.
Time | 10:00-11:00 | Include timezone for external meetings if needed.
Chair | Project Manager | Person who confirms decisions and closes the meeting.
Minute taker | Project Coordinator | Person responsible for issuing the minutes.
Location / link | Online / Meeting room 1 | Meeting room, video link, or reference to calendar invite.
Distribution | Attendees and required stakeholders | List groups or use a controlled distribution list.

## Minutes
Item ID | Agenda item | Discussion summary | Outcome / next step | Owner | Due date | Status | Priority | Follow-up | Related action | Evidence / link | Notes
Item ID | Agenda item | Discussion summary | Outcome / next step | Owner | Due date | Status | Priority | Follow-up | Related action | Evidence / link | Notes
M-001 | Previous action review | Open actions were checked and blockers were identified. | Escalate blocked items before the next meeting. | Project Manager | 2026-05-10 | In progress | High |  | A-001 | Link FileStudio record or document if needed.
M-002 | Approval route | The team discussed approval ownership for deliverable packages. | Decision recorded in the Decision Log. | Discipline Lead | 2026-05-14 | Open | Medium |  | A-002
M-003 | Late input from supplier | Supplier date may affect downstream review. | Track as a risk if no confirmation is received. | Procurement Lead | 2026-05-12 | Open | High |  |  | Can be moved to Risk Register.
Formulas:
Follow-up = IF([Status]="Done","Closed",IF(OR([Owner]="",[Due date]=""),"Check",IF([Due date]<TODAY(),"Overdue",IF([Due date]<=TODAY()+3,"Due soon","On track"))))
Follow-up = IF([Status]="Done","Closed",IF(OR([Owner]="",[Due date]=""),"",IF([Due date]<TODAY(),"Overdue",IF([Due date]<=TODAY()+3,"Due soon","On track"))))

## Decision Log
Decision ID | Source item | Topic | Decision | Owner / authority | Decision date | Status | Follow-up action | Evidence / reference | Notes
Decision ID | Source item | Topic | Decision | Owner / authority | Decision date | Status | Follow-up action | Evidence / reference | Notes
D-001 | M-002 | Approval route | Each deliverable package must show one approval owner. | Project Manager | 2026-05-07 | Agreed | A-002 | Link approval record or controlled minutes if needed.
D-002 | [5 empty] | Proposed

## Action Register
Action ID | Source item | Action | Owner | Assigned date | Due date | Days to due | Status | Priority | Traffic light | Completion date | Evidence / link | Notes
Action ID | Source item | Action | Owner | Assigned date | Due date | 0 | Status | Priority | Traffic light | Completion date | Evidence / link | Notes
A-001 | M-001 | Close all blocked actions or escalate them before the next meeting. | Project Manager | 2026-05-07 | 2026-05-10 |  | In progress | High |  |  | Attach evidence in FileStudio if formal traceability is needed.
A-002 | M-002 | Assign one approval owner for each deliverable package. | Discipline Lead | 2026-05-07 | 2026-05-14 |  | Open | Medium
Formulas:
Days to due = IF([Due date]="","",[Due date]-TODAY())

## Attendees
Name | Organization / team | Role | Attendance | Required for decisions? | Email / contact | Notes
Name | Organization / team | Role | Attendance | Required for decisions? | Email / contact | Notes
Project Manager | Delivery team | Chair | Present | Yes
Project Coordinator | Delivery team | Minute taker | Present | No
Discipline Lead | Design team | Contributor | Present | Yes

## Guidance
Topic | Guidance
Topic | Guidance
Best use | Use Meeting Setup for metadata, Minutes for the narrative record, Decision Log for formal decisions, Action Register for follow-up, and Attendees for distribution.
Functional follow-up | Due dates, Days to due, Traffic light, Status, and Priority make this useful as a working action register after the meeting.
Platform connection | When a decision or action needs evidence, link the relevant controlled document, FileStudio record, task, approval, or workflow reference in Evidence / link.
DocStudio companion | Use the DocStudio Meeting Minutes template when the output needs a formal, print-ready minute document.

## Table Objects
Column A | Column B | Column C
Code | Sheet | Link

## Currencies
Column A | Column B | Column C | Column D
Code | Symbol | Rate vs Main Currency | Main Currency